## Sheet1
BugID | Date Recorded | Short Description | Detais | Assigned to | Status | git commit index
1 | 2014-06-06 | VM launch was still successful even when rpcore crashed. | 1. VM launch was still successful even when rpcore crashed. – the crashing was due to some code in nontpmrpcore has /tmp/rptmp hard-coded, and when it failed to find the directory (new rpcore code has flexibility in looking for tcconfig.xml, no longer requires /tmp/rptmp, but seems still some other code assumes /tmp/rptmp), it crashed. The issue is: when rpcore was not successful, no matter what reasons (return failures, no responses for a long time, etc), VM launch shall be blocked unless it’s audit policy. Is that the default policy now? Or shall the code be improved to block VM launch if rpcore fails. | Ravindra | Fixed? | fix pushed in 06/09
2 | 2014-06-06 | 2. IMVM not invoked by Rpcore. | We found that the issues is that the startApp function doesn't get called on first request but gets called on subsequent requests. On the first such request, we see the logs related to RPCore initialization (that should have been printed at the time of actual initialization of RPCore and not on receiving request for measurement).This used to work earlier, looks like some recent change has broken it, we are looking into it and will need Vinay's help in figuring out the probable changes that caused this issue.
3 | 2014-06-09 | rpquote issue | reported by Mohd | Vinay